## Sheet1
phrase | task | status | pos | start | end
phrase1 | task1 | done | first_1 | 2014-01-06 | 2014-1-8
phrase1 | task2 | active | first_2 | 2014-01-09 | 3d
phrase2 | task3 | crit | sec1 | after first_2 | 5d
phrase2 | task4 | crit | sec2 | after sec1 | 3d